## Homepage
FINEBUY.COM
VERSION: |  |  |  | VERIFIED BY:RUGMA
TESTED BY:ATHIRA MITHUN |  |  |  | DATE: 03.07.2024
ENVIROMENT SET UP:WINDOWS 10 |  |  |  | MODULE NAME:HOME
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
FBS_TC_01 | Check whether the Home page gets loaded easily | 1.Click open the site link | https://shop.finebuy.co.in/ | Should Open Home page successfully without delay | Home was opened without delay | Pass
FBS_TC_02 | Check the site on different browsers (e.g., Chrome, Firefox) and devices (desktop, mobile) to ensure consistent behavior and appearance. | 1.Enter the site name |  | The site should be working fine on all browsers | The site works fine on all browsers | Pass
FBS_TC_03 | Check the site fuctions on different screen sizes and resolutions to ensure usability on various devices. | 1.Enter the site name |  | Should be User friendly and eye pleasing | The site resolution changes on system screens | Fail
FBS_TC_04 | Check if the Page gets loaded quickly without much delay | 1.Click open the site link 2.Clink on any of the butons |  | Pages must be loaded without delay | Pages gets loaded with a delay of 3s-4s | Fail
FBS_TC_05 | Check if the pointer by default changes when pointing towards an active links | 1.Click open the site 2.Hover the cursor on the buttons |  | The Default pointer arrow should change to Link Select pointer | Default arrow Pointer changes to Link selector | Pass
FBS_TC_06 | Check whether the display of the page is well defined | 1.Click open the site link |  | Ecommerce site home page should be attractive | The page contains oversized images | Fail
FBS_TC_07 | Check whether the font used is readable and correctly sized | 1.Click open the site link 2.Scroll across the page |  | All the font used should be readable and appropriate for the page | Some of the font used are not readable and also oversized for the page | Fail
FBS_TC_08 | Check if the page contains any broken elements(images or texts) | 1.Click open the site link |  | The Home page should have no broken elements | The header of the page contains the company logo which is not visible fully | Fail
FBS_TC_09 | Check if the page title is displayed on the top | 1.Click open the site link |  | The headre of the page should contain the title of the site | The page title is shown on the top of the page | Pass
FBS_TC_10 | Check if the page contains other required icons in an ecommerce site | 1.Click open the site link |  | All the important icons should be included in the home page as per an ecommerce site | The icons like User icon, shopping cart, Contactetc are visible | Pass
FBS_TC_11 | Check if home link is accessible from all pages | 1.Click open the site link |  | Home link should be accessible from all pages | Home link is accessible from all pages | Pass
FBS_TC_12 | Check if tool tip is provided for all fields | 1.Click open the site link |  | Tool tip should be provided for all fields | Tool tip provided for all fields in home page | Pass
FBS_TC_13 | Check if the alignment on the home page | 1.Click open the site link 2.Scroll across the page |  | Alignment should be proper | Images are not properly aligned | Fail
FBS_TC_14 | Chechk if the icons are clickable | 1.Click open the site link 2.Click all the icons one by one |  | The icons must be clickable | The icons are clickable | Pass
FBS_TC_15 | Check whether the buttons Login, Cart,given in the home page are clickable | 1.Open the Site 2.Click on the buttons Login 3.Click on th Cart |  | All the buttons should be clickable and should carry the user to the corresponding page | The buttons are clickable and navigation is possible | Pass
FBS_TC_16 | Check if the images on the Home page are clickable | 1.Open the Site 2.Click on the images |  | Images on the Home page should be clickable | Images are clickable | Pass
FBS_TC_17 | Check whether clicking the image directs the user to the product specification page | 1.Open the Site 2.Click on the images |  | Clicking the images should direct to the product specification page | Images are clickable and directs to the product belonging page | Pass
FBS_TC_18 | Check if the buttons navigate to the corresponding pages | 1.Open the Site 2.Click on the buttons |  | All the buttons should carry the user to the corresponding page when clicked | Not all the buttons takes you the corresponding page | Fail
FBS_TC_19 | Check if the hamburger menu "Categories menu" displays all the product categories in the drop down required for an ecommerce site | 1.Open the Site 2.Click on the hamburger menu |  | The Categories menu should display all the product names included in the site | The drop down menu contains all the product name icluded in the site | Pass
FBS_TC_20 | Check whether the Phone icon and a phone given explains the purpose | 1.Open the site |  | The phone number or the icon given on the headr of the page should be denoted with a name or purpose | The phone number or phone icon does not mention the purpose of the same | Fail
FBS_TC_21 | Check if the User icon on the right corner of the page asks for the user login details | 1.Open the site 2.Click on User icon |  | The icon should show Login and password fields for registered Users | The icon shows Username and password fields for login | Pass
FBS_TC_22 | Check if the User profile page is present on Home page | 1.Click open the site link 2.Scroll across the page |  | User profile Page should present | User profile page is present in the name of"My Account" | Pass
FBS_TC_23 | Verify if the shopping cart icon on the home page is actionable | 1.Open the site 2.Click on shopping cart icon |  | Shopping cart icon should direct to the cart page | User navigated to cart page | Pass
FBS_TC_24 | Verify if the shopping cart icon shows the number of products in the cart | 1.Open the site 2.Check the shopping cart icon |  | N of products added in the cart must be shown | Number of products added to the cart was shown without error | Pass
FBS_TC_25 | Check if the button Login on the home page opens a page for New user registration | 1.Open site "Finebuy" 2.Click on Login button |  | The Login page opens a page for logging in for a existing User and create account for anew user | The page contains login field for an existing User and registering for a new user | Pass
FBS_TC_26 | Verify if the no two buttons takes the user to the same page | 1.Open Site 2.Click on Login 3.Click on "My account button" Click on" User icon" |  | All three buttons directed to same page "My Account" for registration for a new User | All the three buttons directs to a common page "My account" which has the registeration field | Pass
FBS_TC_27 | Verify the response of the User icon once user is already registered | 1.Click on User icon |  | A drop down window should be shown two text links My Account and Logout option for a registered User | A drop down window shown with two text links My Account and Logout option for a registered User | Pass
FBS_TC_28 | Check the response of the text buttons below the header like login, cart, sell on Finebuy,About etc | 1.Open site "Finebuy" 2.Click on Login button 3.Click on Cart 4.Click on all other text buttons individually |  | Each button should direct the User to the corresponding page on the same window | Except for the text buttons "Sell on Finebuy" and " About us" all other text buttons opens up in the same window, and the former two open new window respectively | Fail
FBS_TC_29 | Check if the images on the Home page are categorised | 1.Click open the site link 2.Scroll across the page |  | Images given should be categorised | Images are categorised on basis of different criterias | Pass
FBS_TC_30 | Check if the link Google play given in the footer of the page is clickable and navigate | 1.Click on the button "Google Play" |  | Button should direct the User to the Playstore | The button directs to the Playstore for App download | Pass
FBS_TC_31 | Check the response of the link given for Support | 1.Click on the link "support@finebuy.co.in" |  | Link should take you to the page | The Link does not repond on clicking | Fail
FBS_TC_32 | Verify the link Cart in Homepage and check if its an active page | 1.Open Site 2.Click on "Cart" |  | Cart redirects the user to the Cart page where product chosen and other details are given | Clicking the Cart button redirects the page to the active Cart page | Pass
FBS_TC_33 | Verify the link Checkout in Homepage and check if its an active page | 1.Open Site 2.Click on "Checkout" |  | Clicking the button redirects Checkout page where addresses saved will be opted | The page is redirected to Checkout page where saved addresses are linked | Pass
FBS_TC_34 | Check the link Sell on Finebuy and check if its an active page | 1.Open Site 2.Click on "Sell on Finebuy" |  | The page should redirect to the Vendor Registration Page with registration fields and other details | The Page is redirected correctly but the Page contains no content and is inactive | Fail
FBS_TC_35 | Verify the link "Terms and Condition" on Homepage and check if its an active page | 1.Click on "Terms and Condition" |  | Page should be redirected to Terms and Condition page | Page was redirected to Terms and Conditions page | Pass
FBS_TC_36 | Verify the link "Privacy Policy" and check if its an active page | 1.Click on "Privacy Policy" |  | Page should be redirected to Privacy Policy of the Site | Page redirected to Privacy Policy of the Site | Pass
FBS_TC_37 | Verify the link "My Account" and check if its an active page | 1.Click the link "My Account" |  | Page should be redirected to My account page | Page was redirected to My account page and is active | Pass
FBS_TC_38 | Verify the link "Shipping Policy" and check if its active | 1.Click on "Shipping Policy" |  | Clicking the link should direct the user to the corresponding page with the shipping rules the site follows | Shipping Policy page with the shopping rules of the company was shown in the page | Pass
FBS_TC_39 | Verify the link "About us" and check if its active | 1.Click on "About us" |  | "About us" link should direct to the page were the company services and other details are given | "About us" link direct to the page were the company services and other details are given | Pass
FBS_TC_40 | Verify the link "Contact us" and check if its active | 1.Click on "Contact us" |  | "Contact us" link should redirect to the page were company contact details are given | The link correctly redirects to the Contact page | Pass
FBS_TC_41 | Check if the tab works properly | 1.Open site |  | Tab function should work properly | Tab works properly | Pass
FBS_TC_42 | Check if scroll bar works when required | 1.Open site |  | Scroll function should work when required | Scroll bar function works properly | Pass

## Login
MODULE2: REGISTRATION& LOGIN
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
FBS_TC_01 | Check if the Registration page contains all the fields required like Username and Password etc | 1.Click open site 2.Click Login | https://shop.finebuy.co.in/ | Registration page should have mandatory fields like Username and Password | The registration is done using email address and phone number .No Username or password field found | Fail
FBS_TC_02 | Check if the mandatory fields are marked with asterisks in red color | 1.Click open site 2.Click Login |  | Mandatory fields should be marked with asterisks | Mandatory fields are marked with asterisks | Pass
FBS_TC_03 | Check if all the fields in Registration are clickable and editable | 1.Click open site 2.Click Login 3.Click on all fields |  | All fields should be clickable and editable | All the felds in Registration are clickable and editable | Pass
FBS_TC_04 | Check if the email field accepts alphabets, numbers and special characters | 1.Click open site 2.Click Login 3.Input data in field |  | Email id field should accept alphabets, numbers and special characters | Alphabets, numbers and special characters are all accepted | Pass
FBS_TC_05 | Check if the email id field accepts input without "@" | 1.Click open site 2.Click Login 3.Enter email id without "@" | athmiagmail.com | Email field should contain an "@" for it to be an email address | Email Id is accepted only if it contains a "@" | Pass
FBS_TC_06 | Check if the registration is done using email id and password | 1.Click open site 2.Click Login 3.Enter email id 4.Enter phone number 5.Click register | athmia89@gmail.com | For registration email id is given as a link to set a password which will be sent to your email | No mail was sent to the email id | Fail
FBS_TC_07 | Check the response if already registered email id is used | 1.Click open site 2.Click Login | 9745399399 | Should show an error notification email id already registered | Error displayed "Email id already registered.Please login directly" | Pass
FBS_TC_08 | Check if the phone number field accepts more than 10 digits | 1.Click open site 2.Click Login 3.Enter a 12 digit number | 1234567891011 | Phone field should not accept more than 10 digits | Error notification displayed when more than 10 digits entered | Pass
FBS_TC_09 | Verify if the mobile verification asks for an OTP | 1.Click open site 2.Click Login 3.Enter phone number 4.Click Register button | 9745399399 | An OTP should be sent to the phone number used for registration | OTP send to registered mobile number | Pass
FBS_TC_10 | Check if registration can be done using mobile number | 1.Open Login 2.Click on button Sign up with mobile number |  | Signup button should navigate to registration with mobile number page | The Signup button opens up register mobile number page | Pass
FBS_TC_11 | Check if the mobile number field accepts any invalid data other than digits | 1.Open Login 2.Click on button Sign up with mobile number 3.Enter any invalid input other than digits | 9745399*39 | Display error message "invalid data,Please enter a valid phone number" | Error message was displayed for invalid inputs | Pass
FBS_TC_12 | Check if the Same mobile number can be used for registering more than once | 1.Open Login 2.Click on button Sign up with mobile number 3.Enter a valid phone number | 9745399399 | Notification should be given "Mobile number already registered | No error message or warning was shown | Fail
FBS_TC_13 | Check for the Login part,Verify all the fields and buttons present and clickable and editable | 1.Click open site 2.Click Login |  | All the required fields are present and should be clickable | All fields present and are clickable and editable | Pass
FBS_TC_14 | Check if the field name in Login are given correctly | 1.Click open site 2.Click Login |  | Each field is named as per the data they are accepting | No Username is created anywhere | Fail
FBS_TC_15 | Check if the email id and password field accepts valid email id and password | 1.Click open site 2.Click Login | athmia89@gmail.com | Email field accepts a valid email id and password | Fields doesn't accept email id and password. shows error "Invalid username ,use a valid email id instead". Also no email was send to the registered email id to set a password. Both fields shows error. | Fail
FBS_TC_16 | Check if the password has an eye icon to hide and show password | 1.Open Site 2.Click Login 3.Enter Email id and password | aman123@gmail.com aman*1234 | Password should be masked | Password was masked | Pass
FBS_TC_17 | Verify if it shows an error if the fields are kept empty | 1.Click open site 2.Click Login |  | Error should be shown if fields are kept empty | Shows error when fields kept empty | Pass
FBS_TC_18 | Check if the checkbox for Remember me field is clickable | 1.Click open site 2.Click Login 3.Click on the checkbox |  | Checkbox given shoukd be clickable | Tick mark appears in the checkbox when clicked | Pass
FBS_TC_19 | Verify if the Lost your password link functionality | 1.Click open site 2.Click Login 3.Click on the "Lost your password " link |  | Clicking the link should direct the user to create new password page | Clicking the link directs the user to a new page where Username or email id is asked to reset password | Pass
FBS_TC_20 | Verify if the Reset password page fields and functions | 1.Click open site 2.Click Login 3.Click on the "Lost your password " link |  | Reset Password should have mail id, old password, new password fields to reset the password. Or the email id given should act as a link to create a new password | Clicking the link directs the user to a new page where Username or email id is asked along with a notification "Lost your password? Please enter your username or email address. You will receive a link to create a new password via email." But no mail is received at the user side and hence password reset option doesn't work. | Fail
FBS_TC_21 | Check for the button "Login with OTP" | 1.Click open site 2.Click Login 3.Click on the "Login with OTP" |  | Clicking Login with OTP should ask for a previously registered mobile number | Clicking Login with OTP asks for a previously registered mobile number | Pass
FBS_TC_22 | Check if the mobile number accepts an unregistered mobile number | 1.Click open site 2.Click Login 3.Click on the "Login with OTP" 4.Enter unregistered mobile number | 9897399399 | An error should be displayed | An error was displayed "Your number is not registered" | Pass
FBS_TC_23 | Check if the mobile number field accepts valid mobile numbers only | 1.Click open site 2.Click Login 3.Click on the "Login with OTP" 4.Enter some characters, symbols or a number with more than 10 digits | asdf123, 98874563210 | An error should be displayed when any input other than an valid mobile number is entered | Aerror message is displyed "verify the input" | Pass
FBS_TC_24 | Check if a field for entering OTP is displayed when "login with OTP" is clicked | 1.Enter mobile number 2.Click on "Login with OTP" | 9895399399 | A field for entering OTP or verification code should be shown | A field for entering OTP was displayed | Pass
FBS_TC_25 | Check if an OTP is send to the registered mobile number for verification | 1.Enter mobile number 2.Click on "Login with OTP" | 9895399399 | An OTP should be send to the registered mobile number | An OTP was sen to the registered mobile number | Pass
FBS_TC_26 | Verify if the OTP has a time limit | 1.Enter mobile number 2.Click on "Login with OTP" | 9895399399 | OTP should have a time limit for security concerns | OTP need to be entered within 30 sec | Pass
FBS_TC_27 | Verify the response for entering wrong OTP | 1.Enter mobile number 2.Click on "Login with OTP" 3.Enter OTP | 9895399399 2301 | Error message should be displayed for entering wrong verification code | Error message was displayed for entering wrong OTP | Pass
FBS_TC_28 | Verify the response when a successful registration is done |  |  | User profile should be created | User profile created and the related data os shown in My Account page | Pass
FBS_TC_29 | Verify if the User have a Logout option | 1.Open Site 2.Click Login 3.Login withOTP 4.Enter OTP 5.Click the User icon 6.Select Logout option | 9895399399 2623 | Once Logged in user should have an option to Logout | Logout link is given in the dropdown of User icon | Pass
FBS_TC_30 | Verify if the User gets logged out if window gets closed | 1.Open Site 2.Click Login 3.Login withOTP 4.Enter OTP 5.Close window 6.Reopen Site 7.Click User icon | 9895399399 4272 | User should be asked to Login unless user have chosen Remember me option previously | User gets Logged out automatically when window gets closed unless user have chosen Remember me option previously | Pass

## Profile
MODULE 3: PROFILE
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
FBS_TC_01 | Verify the text links in the page "My Account" if readable and properly aligned |  |  | All the links given should be readable and properly aligned | All the links are readable and properly aligned | Pass
FBS_TC_02 | Verify if the text links are clickable | 1.Click open Site 2.Click "My Account" 3.Click all the links |  | All links given should be clickable | All links are clickable | Pass
FBS_TC_03 | Verify if only registered users can accesss this page | 1.Click open Site 2.Click "My Account" |  | Only registered users should be able to access this page | Only registered users can view and access this page | Pass
FBS_TC_04 | Check the first link option in the My account page which is "Dashboard" | 1.Open My account 2.Click Dashboard |  | Dashboard should showcase all the recent orders,Shipping and billing details, edit password option, edit account details etc | All the details regarding the User's recent orders,shipping nd billing are given.Also edit password and edit account details is possible | Pass
FBS_TC_05 | Check the 2nd link option given in the My account page which is "Order" | 1.Open My account 2.Click Order |  | Order page shoiuld be showcasing all the orders made by the user | Order page shows all the product details | Pass
FBS_TC_06 | Check the page for a new user | 1.Open My account 2.Click Order |  | The page should display "No order has been made yet" | Displays "No order has been made yet" | Pass
FBS_TC_07 | Verify the link Addresses which will be used while checkout | 1.Open My account 2.Click Addresses |  | The page should have addresses saved or option to add addresses | The page shows the addresses saved.Also has an option to add addresses | Pass
FBS_TC_08 | Verify if the Add link is clickable and becomes active when pointed by cursor | 1.Open My account 2.Click Addresses 3.Hover thepointer over the link Add |  | The link is clickable,also An active link should be shown in blue when pointer is hovered over it | When hovered over the link it turns blue showing it to be active and is clickable | Pass
FBS_TC_09 | Verify if clicking the Add link redirects you to page Billing addresses | 1.Open My account 2.Click Addresses 3.Click Add |  | Add link should direct to a page with fields for adding addresses | Page navigates to Billing Address | Pass
FBS_TC_10 | Check whether the address page has all required fields | 1.Open My account 2.Click Addresses 3.Click Add |  | All required fields should be available | All the fields necessary for the address are present | Pass
FBS_TC_11 | Check if the phone number and email id used while registering gets filled in automatically | 1.Open My account 2.Click Addresses 3.Click Add |  | Phone number and Email id used while registering should get filled automatically | Phone Number and email id are filled in automatically when the page is opened | Pass
FBS_TC_12 | Check if all the mandatory fields are marked with a red asterisk | 1.Open My account 2.Click Addresses 3.Click Add |  | All mandatory shoulkd be marked by a red asterisk | Mandatory fields are marked with asterisks | Pass
FBS_TC_13 | Check if the name field accepts only characters as input | 1.Click Addresses 2.Click edit 3.Enter input data other than characters | 1234*16 | The first and last name field in the Address page should be accepting Characters | The first and last name field in the Address page accept Characters, numbers and symbols | Fail
FBS_TC_14 | Check if Country field has a drop downlist to choose | Click on Country field | India | The drop down list should show different countries | Country is chosen from the dropdown list | Pass
FBS_TC_15 | Check if the Country field is editable | Click on Country field |  | The field should not be editable | The country field is not editable | Pass
FBS_TC_16 | Check if the tab function works for moving into the next field | Click tab |  | Tab function be working | Tab function works | Pass
FBS_TC_17 | Check if the street address field accepts numbers as well as characters | Enter the street address |  | Street address field should accept both numbers and characters | Numbers and characters are both accepted in this field | Pass
FBS_TC_18 | Check if the field State is a dropdown list | click on State field |  | State field is dropdown list | Shows dropdown list to choose the state | Pass
FBS_TC_19 | Check if the pin code field accepts only numbers as input | Entrer "asdfgh" |  | Pincode field should accept only numbers and should show an error when characters are entered | Shows error when characters are entered | Pass
FBS_TC_20 | Check ifv the save address button is clickable | Click on Save address |  | Save Address button should be clickable | Button Save Address is cickable | Pass
FBS_TC_21 | Check if the page easily navigates back to the My account page | Click on Save address |  | The page should redirect back without any error | The billing address page is redirected back to My Account page with ease | Pass
FBS_TC_22 | Check if all the data entered on the Address fields are correctly displayed in the Addresses page |  |  | Address dissplayed should be the same data entered in the Billing address fields | Address is correctly displayed | Pass
FBS_TC_23 | Check if more than one address can be saved | 1.Open My account 2.Click Addresses 3.Click Add 4.Enter the Address | H no:9 william Street Cochin | There should be an option to save more than one address | Only one address can be saved for a User | Fail
FBS_TC_24 | Verify if the page has an edit option to make any changes for the saved address | 1.Click Addresses |  | An edit option should be available for making any changes in the Address saved | An edit option is available | Pass
FBS_TC_25 | Verify the next link "Account details" if a page with User data is shown | 1.Click open "Account details" |  | Account details page should show the user details | Account detail page shows the Username and password | Pass
FBS_TC_26 | Check if the user can make changes to First name,last name,and display name | 1.Click on the fields First name, last name, display name |  | All the fields should be editable | All the fields are editable | Pass
FBS_TC_27 | Check if the fields are mandatory and are marked by a red asterisk | 1.Click open "Account details" |  | Error should be shown if fields are kept empty and mandatory fields should be marked by ed asterisk | Error is shown when fields are kept empty and also mandatory fields are marked | Pass
FBS_TC_28 | Check if the email id and password fields are also mandatory | 1.Click open "Account details" |  | Email and password fields should be mandatory | Email is marked mandatory but password is not marked | Fail
FBS_TC_29 | Verify if the password can be changed | 1.Click open "Account details" |  | There should be an option to reset the password(if in use) | Password can be reset | Pass
FBS_TC_30 | Verify the fields to reset password are editable and masked | 1.Click open "Account details" |  | The password reset fields should be editable and masked | The password reset fields are editable and masked | Pass
FBS_TC_31 | Verify if the password fields have an eye icon on each fields clicking by which the password become visible | 1.Click open "Account details" |  | Password should have eye icon clicking by which the password become visible | Eye icon are present on all password reset fields | Pass
FBS_TC_32 | Verify if the eye icons are clickable | 1.Click open "Account details" |  | Eye icons should be clickable | Eye icons are clickable | Pass
FBS_TC_33 | Verify if the new password field checks the strength of the password and displays it | 1.Enter new password | 12as*as34 | The strength of the password should display as weak, medium and strong | The password strength is shown as the user enters the password | Pass
FBS_TC_34 | Check if the password field has a character limit or criteria | 1.Enter Password | asdef124365*& | The password field should have a character limit and criteria | No character limit or particular criteria is mentioned | Fail
FBS_TC_35 | Check if copy and paste function works on the Password fields | 1.Enter Password 2.Ctrl+C copy the password 3.Ctrl+V Paste the password | asdef124365*& | Copy and Paste functions should not be used in password fields | Copy and Paste functions well in password fields | Fail
FBS_TC_36 | Check if the Save changes button saves the new password and shows a notification of successfully resetting password | 1.Click Save changes |  | Changes should be saved and user must be notified of successfully resetting the password | Changes saved and User notified of Successfully resetting password | Pass
FBS_TC_37 | Verify the link "Logout" if the User can logout from the page without any issue | 1.Click Logout |  | User should be succesfully logged out and redirected to the login page | User was succesfully logged out and redirected to the login page | Pass
FBS_TC_38 | Verify if logging out from one device affects the login status on the other device where the same account is logged in | 1.Click Logout |  | Once logged out from one device the user should be logged off from all the devices being in use | Once logged out from one devices the user gets logged off from all the devices being in use | Pass

## Search&Product
MODULE 4: SEARCH & PRODUCT
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
FBS_SR_01 | Verify if the Search bar is clearly visible on the Home page | 1.Click open site | https://shop.finebuy.co.in/ | Search bar should be clearly visible in Home page | Search bar is clearly visible in Home page | Pass
FBS_SR_02 | Verify if it gets loaded easily fof every search entry | 1.Open site 2.Enter a query |  | search result should be loaded without delay | Search result page takes time to get loaded everytime when a query is entered | Fail
FBS_SR_03 | Verify if the Search bar accepts alphabets,numbers or symbols | 1.Click open site 2.Enter the product name | tshirt10 | Search bar should accept alphabets numbers and symbols | Search bar accepts alphabets numbers and symbols | Pass
FBS_SR_04 | Check whether entering a valid product name directs the user to the relevant page | 1.Click open site 2.Enter the product name | tshirt11 | Search option should direct the user to the corresponding product page | User is directed to the relevant product page | Pass
FBS_SR_05 | Check the response when an invalid data is provided | 1.Click open site 2.Enter an invalid data | acdsdc | Should display an error | Displays an error notifying "No match found" | Pass
FBS_SR_06 | Verify that the search is performed as per the search query | 1.Open site 2.Enter a query |  | search result should be as per the search query | Search results are as per the queries | Pass
FBS_SR_07 | Verify that search suggestions (autocomplete) appear as the user types. | 1.Click open site 2.Enter the product name |  | Search should autocomplete the terms for an efficient performance | Autocomplete doesnot work in Search bar | Fail
FBS_SR_08 | Verify if search with synonyms or related terms and verify if relevant products are displayed | 1.Open site 2.Enter data in search bar |  | Any related terms should display all relevant products available | All products are shown even when related terms are entered | Pass
FBS_SR_09 | Verify if the search bar is prominently displayed and easily accessible from any page within the site | 1.Click open site |  | Search bar should be clearly displayed and easily accessible from any page within the site | Search bar is easily accessible from any page within the site | Pass
FBS_SR_10 | Check the response of search results(for eg. Pagination and infinite scroll ) when large number of results are returned | 1.Open site 2.Enter data in search bar |  | search result should have pagination and infinite scroll like features when large number of results are returned | Search results have pagination and infinite scroll features | Pass
FBS_SR_11 | check if search result can be filtered on basis of brands,price,reviews and ratings | 1.Open the site 2.Enter search data 3.click search icon |  | Filter option sould be present for filtering the products | Search result has filter option for searching | Pass
FBS_SR_12 | Check if the search result page has pagination and scroll options in case of large results | 1.Open the site 2.Enter search data 3.click search icon |  | Pagination and scroll options should be present in search result in case of large results | Pagination and scroll options are given | Pass
FBS_SR_13 | Check if the search result page has sorting options on basis of popularity,price,rating | 1.Open the site 2.Enter search data 3.click search icon |  | Sorting option on basis of popularity price and rating should be present for easing shopping | Sorting options are present | Pass
FBS_SR_14 | Verify if the products are displayed properly | 1.Open the site 2.Enter search data 3.click search icon |  | All the products as per the search query should be displayed properly | All products afe displayed properly | Pass
FBS_SR_15 | Verify if the price of the product is displayed correctly in a readable format | 1.Click on the product |  | The product price should be displayed correctly | Product price is displayed clearly | Pass
FBS_SR_16 | Verify if the discounted rates for each products given are also correct | 1.Click on the product |  | Actual price and discounted rate shoud be correctly given | Discounted rates doesnot tally with the discounts provided | Fail
FBS_SR_17 | Verify if product reviews are mentioned and also user has an option to write a review | 1.Click on the product |  | Reviews should be mentioned and also user should have an option to write a review for a product | Reviews are mentioned and write review option is available | Pass
FBS_SR_18 | Verify if the stock in/stock in ,size etc are given | 1.Click on the product |  | Stock in/stock out ,size etc shoukd mentioned along with the product | Stock in /stock out, size etc are displayed | Pass
FBS_SR_19 | Verify if specification is given for every product | 1.Click on the product 2.Click on specification |  | Specification should be provided in the specification link | Specification not available in under the specification link.Specification page empty instead specifications are given under description link | Fail
FBS_SR_20 | Verify if the specification given are correct and complete | 1.Click on the product 2.Click on description link |  | Specification given for all items should be correct complete | Some items have incomplete descriprions | Fail
FBS_SR_21 | Verify if the zoom in/zoom out works properly | 1.Click on the product |  | Zoom in/zoom out option shoulkd help user check the product properly | Zoom in/zoom out doesnot work properly | Fail
FBS_SR_22 | Verify if shipping information are given along with the product | 1.Click on the product |  | Shipping information should be provided along with the product | shipping information not given along with product | Fail
FBS_SR_23 | Verify if the payment options are provided | 1.Click on the product |  | Payment options should be given along with the product | Payment options not given | Fail
FBS_SR_24 | Verify if product suggestions are given | 1.Click on the product |  | Product suggestions should be displayed | Product suggestions are displayed | Pass
FBS_SR_25 | Verify if the buttons quantity ,add to cart,on the page is properly displayed | 1.Click on the product |  | All buttons should be working and properly displayed | Buttons quantity and add toncart overlaps | Fail
FBS_SR_26 | Check the response of the button 'buy it now' | 1.Click on the product 2.click on buy it now |  | Buy it now button should direct the user to the payment page | When clicked an error message shows if the product is already in the cart and does not direct to the Payment page | Fail
FBS_SR_27 | Verify if the search for products with similar names or descriptions differentiates the products | 1.Click on the product |  | Search should differentiate the items even with similar names or descriptions | Differentiates the items | Pass

## cart & payment
MODULE 5: CART & PAYMENT
TEST ID | TEST DESCRIPTION | TEST PROCEDURE | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS
FBS_TC_01 | Verify that when user clicks on add to cart, the product should be added to cart. | 1.Click on add to cart |  | Clicking the add to cart button should display it in the cart | Clicking the add to cart button adds the product successfully | Pass
FBS_TC_02 | Verify that user should be able to continue shopping after adding items to cart. | 1.Click on add to cart |  | User should be able to do shopping after adding items to cart | User is able to continue shopping after adding items to cart | Pass
FBS_TC_03 | Verify that item quantity should be increased if user adds same item in cart again. | 1.Click on add to cart for different products |  | The quantity should increase if the user adds same item in the cart | The quantity of items gets increased when items added to the cart | Fail
FBS_TC_04 | Verify that total amount of all items should be displayed to user. | 1.Click on add to cart 2.click open cart |  | The total amount of all items shoulkd be displayed in the shopping cart page | In Shopping cart total amount of all the items are displayed | Pass
FBS_TC_05 | Verity that the amount displayed to user should include the taxes and shipping charges as per location. | 1.Click open Cart |  | The amount displayed should include taxes and shipping charges as per location | The cart displays amount including taxes and shipping charges as per location | Pass
FBS_TC_08 | Verify that user should be able to apply coupons or vouchers at checkout from cart. | 1.Click open Cart |  | User should be able to apply coupons or vouchers at checkout from cart | Coupons and vouchers are applicable | Pass
FBS_TC_09 | Verify that items in cart should be present if user logs out and logs in again. | 1.Click open Cart 2.Add items 3.Logout 4.Login again |  | The items in the cart should be present even if the user logouts | Items remains in the cart even after logging out | Pass
FBS_TC_10 | Verify if proceeding to the checkout page is available in the cart | 1.Click open Cart 2.Add items |  | Shopping cart should also contain proceed to checkout option | Cart do have the option to proceed with checkout process | Pass
FBS_TC_11 | Verify that all items, quantities, and prices are accurately transferred to the checkout page. | 1.Click open Cart 2.Add items 3.Click on proceed to checkout |  | All items,quantities and prices should be accurately transferred to the checkout page | All details are transferred to the checkout page | Pass
FBS_TC_12 | Verify the response when attempt to add items in quantities that exceed available stock to validate error messages and handling of stock limits. | 1.Click open Cart 2.Add items |  | Error message should be displayed when Out of stock items are added to cart | A notification is given while attempting to add limited stocks | Pass
FBS_TC_13 | Verify if different shopping options are shown along with the product | 1.Click open Cart 2.Add items |  | Every product should have shopping options mentioned along with them | Shopping options are not mentioned along with products | Fail
FBS_TC_14 | Verify that payments options applicable for the order should be displayed at checkout. | 1.Click Checkout button |  | Checkout page should display all the payment options available | All the payment options are displayed | Pass
| Verify if the delivery details are displayed along with the products at the checkout page | 1.Click Checkout button |  | The checkout page displays the delivery details along with the product | Delivery details are displayed | Pass
FBS_TC_16 | Verify that user should get order details by message or email. | 1.Click Checkout button 2.Proceed payment 3.Enter details 4.confirm payment | Payment details | A message or email with order details should be received by the user after confirmed payment | A message is received at the registered mobile number | Pass
FBS_TC_17 | Verify that user should be directed to home page after checkout. | 1.Click Checkout button |  | The user should be directed to home page after checkout | The user is directed to the Homepage | Pass
FBS_TC_18 | Verify if the checkout page have an option to add more than one delivery address | 1.Click Checkout button |  | The user should be able to add an additional address | No option is given for adding an additional address | Pass
FBS_TC_19 | Verify that user details should be displayed on payment page for registered customers. | 1.Click Checkout button |  | The user details should be given on the checkout page | User details are displayed on the checkout page | Pass
FBS_TC_20 | Verify that on successful payment email or text message should be delivered to customer along with unique order number. | 1.Click Checkout button 2.Confirm order |  | An email or text message should be received on succesful payment completion | An email and text message is received after successful completion of the transaction | Pass
FBS_TC_21 | Verify the option the shipping charges and other charges if applied | 1.Click Checkout button |  | Places with free shipping should be differentiated | Even if it says the user in free shipping zone, shipping charge is added | Fail
FBS_TC_23 | Check if the payment options are selectable | 1.Click Checkout button |  | User should be able to choose the payment option | Payment options are selectable | Pass
FBS_TC_24 | Check if the the currect amount and currency is shown on the page | 1.Click Checkout button |  | Correct amount and currency should be displayed on the page | Correct amount and currency is displayed on the page | Pass
FBS_TC_25 | Check if it accepts cash on delivery | 1.Click Checkout button |  | Cash on delivery option should be available | Cash on delivery details are available | Pass
FBS_TC_26 | Check if the credit card number is masked | 1.Click Checkout button 2.Select the payment option |  | The credit card number should be masked | The credit card number is masked | Pass
FBS_TC_27 | Check if the page have any mandatory field to be filled | 1.Click Checkout button 2.Select the payment option |  | All mandatory fields should be marked and filled for the transaction to complete | All mandatory fields are marked and filled for payment to get completed | Pass
FBS_TC_28 | Check if an error message is shown if the fields are kept empty | 1.Click Checkout button 2.Select the payment option |  | An error message should be shown if mandatory fields are kept empty | An error message is shown when mandatory fields are kept empty | Pass
FBS_TC_29 | Check if the mm/yy and CVV fields accepts inputs and CVV should be masked in case of debit card | Enter banking details |  | All fields should aacepts input and the CVV should be masked for security reasons | Inputs are accepted and CVV is masked | Pass
FBS_TC_30 | Verify if an a cancel order button is available | Check the checkout page |  | A cancel order button should be present | Option for cancelling an order is available | Pass
FBS_TC_31 | Verify if the previous transaction details are displayed in the orders page | Check the orders page |  | Previous transactions shpuld be displayed in the oreders page | Previous orders can be tracked from the orders page | Pass
FBS_TC_32 | Verify if the cart gets emptied after the transaction completion | Check the cart |  | The cart should get emptied after successful trasaction completion | The cart gets gets emptied after transactio completion | Pass
FBS_TC_33 | Verify if there is a return option for the order | Check the transaction page |  | A return option should be available | Return option is available | Pass
FBS_TC_34 | Verify if there is an option for refund | Check the transaction page |  | An option for refund should be available | Refund option is available | Pass

## DEFECT REPORT
DEFECT REPORT -FINEBUY.COM
IDENTIFIED BY:ATHIRA MITHUN REPORTED TO:
REPORTED TO:RUGMA
ENVIRONMENT DETAILS:WINDOWS 10
DATE:03.07.2024
BUG ID | EXPECTED RESULT | BUG DESCRIPTION | STEPS TO REPRODUCE | SEVERITY | PRIORITY | SCREENSHOT | STATUS
DEF_FBS_01 | The site should function on different screen sizes and resolutions to ensure usability on various devices. | The site resolution changes on system screens.Images displayed are like zoomed in | 1.Enter the site name | Minor | Low |  | New
DEF_FBS_02 | The Page should get loaded quickly without much delay | Pages gets loaded with a delay of 3s-4s | 1.Enter the site name 2.Click on any live button | Minor | High |  | New
DEF_FBS_03 | The display of the page should be well defined | The page contains oversized images anfd is crowded | 1.Enter the site name | Enhancement | Medium | display.png | New
DEF_FBS_04 | The font used shoud be readable and correctly sized | Some of the font used are not readable and also oversized for the page | 1.Enter the site name 2.scroll across the page | Minor | Medium | display.png | New
DEF_FBS_05 | The page should not contain any broken elements(images or texts) | The header of the page contains the company logo which is not visible fully | 1.Click open the site link | Minor | Low | logo.png | New
DEF_FBS_06 | The alignment on the home page should be proper | Images are not properly aligned | 1.Click open the site link 2.scroll across the page | Enhancement | Low | alignment.png | New
DEF_FBS_07 | The buttons should navigate to the corresponding pages | Not all the buttons takes you the corresponding page | 1.Click open the site link 2.Click on all buttons | Major | High |  | New
DEF_FBS_08 | The Phone icon and a phone number given should explain the purpose | The phone number or phone icon does not mention the purpose of the same | 1.Click open the site link 2.scroll to see the header of the page | Major | Low | Screenshot 2024-06-29 091900.png | New
DEF_FBS_09 | The text buttons in the home page header like login, cart, sell on Finebuy,About etc should not open in a new window everytime | Except for the text buttons "Sell on Finebuy" and " About us" all other text buttons opens up in the same window, and the former two open new window respectively | 1.Enter the site name 2.Click on all text buttons | Major | High | sellonfine.png | New
DEF_FBS_10 | All the link given should work properly | The Support Link does not repond on clicking | 1.Open the site 2.Click on Support | Major | High |  | New
DEF_FBS_11 | Registration page should have mandatory fields like Username and Password | The registration is done using email address and phone number .No Username or password field found | 1.Click open site 2.Click Login | Major | Low |  | New
DEF_FBS_12 | For registration email id is given as a link to set a password which will be sent to your email | No mail was sent to the email id to generate a password. | 1.Click open site 2.Click Login 3.Enter email id 4.Enter phone number 5.Click register | Major | High | Screenshot 2024-06-22 P8.png | New
DEF_FBS_13 | Notification should be given "Mobile number already registered if the Same mobile number is used for registering more than once | No error message or warning was shown | 1.Open Login 2.Click on button Sign up with mobile number 3.Enter a valid phone number | Minor | Medium |  | New
DEF_FBS_14 | The field name in Login are given correctly .Each field is named as per the data they are accepting | No Username is created anywhere | 1.Click open site 2.Click Login | Major | High | Screenshot 2024-06-22 p7.png | New
DEF_FBS_15 | Email field accepts a valid email id and password | Fields doesn't accept email id and password. shows error "Invalid username ,use a valid email id instead". Also no email was send to the registered email id to set a password. Both fields shows error. | 1.Click open site 2.Click Login | Major | High | Screenshot 2024-06-22 p7.png | New
DEF_FBS_16 | Reset Password should have mail id, old password, new password fields to reset the password. Or the email id given should act as a link to create a new password | Clicking the link directs the user to a new page where Username or email id is asked along with a notification "Lost your password? Please enter your username or email address. You will receive a link to create a new password via email." But no mail is received at the user side and hence password reset option doesn't work. | 1.Click open site 2.Click Login 3.Click lost your password | Major | High | Screenshot 2024-06-22 p9.png | New
DEF_FBS_17 | The first and last name field in the Address page should be accepting Characters | The first and last name field in the Address page accept Characters, numbers and symbols | 1.Click open site 2.Login with OTP 3.Add Address | Major | High | Screenshot 2024-07-03 114618.png | New
DEF_FBS_18 | There should be an option to save more than one address | Only one address can be saved for a User | 1.Click open site 2.Login with OTP 3.Edit Address | Minor | Medium | address.png | New
DEF_FBS_19 | Email and password fields should be mandatory for Registration | Email is marked mandatory but password field not given for Registration and other option provided but that also not working | 1.Click open site 2.Click Login 3.Enter email id | Minor | High | nopasswd.png | New
DEF_FBS_20 | The password field should have a character limit and criteria | No character limit or particular criteria is mentioned | 1.Open site 2.Click Login 3.Enter email id 4.Enter password | Major | High | password limit.png | New
DEF_FBS_21 | Copy and Paste functions should not be used in password fields | Copy and Paste functions well in password fields | 1.Open site 2.Click Login 3.Enter email id 4.Enter password | Major | High |  | New
DEF_FBS_22 | Search result should be loaded without delay | Search result page takes time to get loaded everytime when a query is entered | 1.Open Site 2.Click on Search bar 3.Enter data | Minor | High |  | New
DEF_FBS_23 | Search should autocomplete the terms for an efficient performance | Autocomplete doesnot work in Search bar | 1.Open Site 2.Click on Search bar 3.Enter data | Enhancement | Medium |  | New
DEF_FBS_24 | Actual price and discounted rate shoud be correctly given | Discounted rates doesnot tally with the discounts provided | 1.Open Site 2.Click on Search bar 3.Enter data "Shirt" 4.Products displays | Minor | High | discountrate.png | New
DEF_FBS_25 | Specification should be provided in the specification link | Specification not available in under the specification link.Specification page empty instead specifications are given under description link | 1.Open Site 2.Search for product 3.Click on Specification | Minor | High | Screenshot 2024-06-30 174726.png | New
DEF_FBS_26 | Specification given for all items should be correct complete | Some items have incomplete descripritons. | 1.Open Site 2.Search for product 3.Click on Specification | Enhancement | High | Screenshot 2024-06-30 174652.png | New
DEF_FBS_27 | Zoom in/zoom out option shoulkd help user check the product properly | Zoom in/zoom out doesnot work properly on all products | 1.Open Site 2.Search for product 3.Click on Specification | Enhancement | High |  | New
DEF_FBS_28 | Shipping information should be provided along with the product | shipping information not given along with product | 1.Open Site 2.Click on Search bar 3.Enter data "Shirt" 4.Products displays | Minor | Medium | prodprob.png | New
DEF_FBS_29 | Payment options should be given along with the product | Payment options not given | 1.Open Site 2.Click on Search bar 3.Enter data "Shirt" 4.Products displays | Minor | Medium | prodprob.png | New
DEF_FBS_30 | All buttons should be working and properly displayed | Buttons quantity and add to cart overlaps in some product cases | 1.Open Site 2.Click on Search bar 3.Enter data "Shirt" 4.Products displays 5.Check add to cart button | Minor | High | Screenshot 2024-06-27 221927.png | New
DEF_FBS_32 | The no of items should increase if the user adds an item to the cart | The quantity of items gets increased when items added to the cart | 1.Open Site 2.Click on Search bar 3.Enter data "Shirt" 4.Products displays 5.Add to cart | Enhancement | Low | Screenshot 2024-06-29 224810.png | New
DEF_FBS_33 | Every product should have shopping options mentioned along with them | Shopping options are not mentioned along with products | 1.Open Site 2.Click on Search bar 3.Enter data "Shirt" 4.Products displays 5.Add to cart 6.Click on cart | Minor | Medium | Screenshot 2024-06-29 224810.png | New
DEF_FBS_34 | Places with free shipping should be differentiated | Even if it says the user in free shipping zone, shipping charge is added | 1.Click on Shopping Cart | Minor | High | Screenshot 2024-06-30 184324.png | New

## TEST REPORT
TEST REPORT
Module No. | Module Name | Test case passed | Test cases failed | Total no.of cases excuted
1 | Home | 31 | 11 | 42
2 | Login | 24 | 6 | 30
3 | Profile | 33 | 5 | 38
4 | Search & Products | 17 | 10 | 27
5 | Cart & Payment | 31 | 3 | 34

## DEFECT DISTRIBUTION
MODULE NAME | DEFECT DISTRIBUTION
HOME PAGE | 11
LOGIN | 6
PROFILE | 5
SEARCH & PRODUCT | 10
CART & PAYMENT | 3
x